Manhattan Quiet Place Finder – Project Timesheet

Project Duration

Start Date: 25 May 2026

End Date: 31 July 2026

Total Estimated Effort: 335 Hours

| Week | Date Range | Major Activities | Estimated Hours |
| --- | --- | --- | --- |
| Week 1 | May 25 – May 31 | Requirements gathering, stakeholder analysis, user research, initial backlog creation | 30 hrs |
| Week 2 | Jun 1 – Jun 7 | User stories, wireframes, Figma prototype, system architecture planning | 35 hrs |
| Week 3 | Jun 8 – Jun 14 | UI/UX refinement, frontend setup, database design, API planning | 35 hrs |
| Week 4 | Jun 15 – Jun 21 | Frontend development, backend development, data source identification | 40 hrs |
| Week 5 | Jun 22 – Jun 28 | Frontend implementation, API development, data collection and processing | 40 hrs |
| Week 6 | Jun 29 – Jul 5 | Backend integration, database implementation, machine learning model development | 40 hrs |
| Week 7 | Jul 6 – Jul 12 | ML model refinement, frontend-backend integration, mobile optimisation | 35 hrs |
| Week 8 | Jul 13 – Jul 19 | System testing, bug fixing, usability testing, feature completion | 35 hrs |
| Week 9 | Jul 20 – Jul 26 | Integration testing, CI/CD deployment, sprint review preparation | 25 hrs |
| Week 10 | Jul 27 – Jul 31 | Final testing, documentation, presentation preparation, project submission | 20 hrs |

Work Package Breakdown

| Work Package | Total Hours |
| --- | --- |
| Requirements Analysis | 25 hrs |
| UI/UX Design | 40 hrs |
| Frontend Development | 55 hrs |
| Backend Development | 55 hrs |
| Data Collection & Processing | 35 hrs |
| Machine Learning Development | 25 hrs |
| Mobile Optimisation | 25 hrs |
| Testing & Quality Assurance | 30 hrs |
| CI/CD & Deployment | 20 hrs |
| Project Management & Scrum Activities | 25 hrs |
| Total | 335 hrs |

Detailed Weekly Allocation

| Work Package | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Analysis | 20 | 5 | - | - | - | - | - | - | - | - | 25 |
| UI/UX Design | 5 | 20 | 15 | - | - | - | - | - | - | - | 40 |
| Frontend Development | - | - | 5 | 15 | 20 | 10 | 5 | - | - | - | 55 |
| Backend Development | - | - | 5 | 15 | 15 | 15 | 5 | - | - | - | 55 |
| Data Collection & Processing | 5 | 5 | 5 | 5 | 10 | 5 | - | - | - | - | 35 |
| Machine Learning Development | - | - | - | - | 5 | 10 | 10 | - | - | - | 25 |
| Mobile Optimisation | - | - | - | - | - | 5 | 10 | 10 | - | - | 25 |
| Testing & QA | - | - | - | - | - | - | 5 | 10 | 5 | - | 20 |
| CI/CD & Deployment | - | - | - | - | - | - | - | 5 | 5 | 5 | 15 |
| Project Management | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | - | 25 |
| Weekly Total | 35 | 35 | 35 | 40 | 55 | 50 | 40 | 35 | 25 | 5 | 340* |

*Minor adjustments can be made during sprint execution to maintain the planned total effort of approximately 335 hours.

Gantt Chart